## SE-related Issues
Issue # | Date Opened | Issue Description | PTR / CR / WR/ESV | Status | Scheduled Delivery Date | Comments
26 | 2015-06-04 | Broker reference data in the "B" record: User data submitted in the "B" record positions 60-80, does not populate in subsequent SX messages when a CBP initiated correction is performed. |  | Open |  | Developers are researching why the user data does not populate on CBP initiated corrections.
25 | 2015-04-30 | SO Messages are not being sent: ACR is not posting the 1C to ocean bills of lading or generating SO messages when the Ocean Entry consist of multiple bills of lading. |  | Open |  | Researching the cause.
24 | 2015-04-30 | SO60 Message, Docs required Sent to Filer: When disposition code 96 is sent to the filer in the SO message, there is not a follow up message advising the filer the specific document that is being requested by CBP. |  | Open |  | Currently being reviewed for resolution.
23 | 2015-04-29 | Piece counting duble posting to ocean bills of lading: Several filers, when using th "U" update action code, has triggered a double posting of the piece count to ocean bills of lading. |  | Open |  | Currently researching the cause of this issue. Developers are unable to duplicate this issue. Will have to continue reporting this issue as it occurs.
22 | 2015-04-24 | Entry Cancelled without input from filer: ACE Cargo Release will show an entry in cancelled status if two SE inputs are received seconds apart. |  | Open |  | Need to research why the system is showing the entry in a cancelled status. Testing possible scenarios to duplicate this issue.
21 | 2015-04-24 | Importer number Encryption: ACE Cargo Release does not support CBP provided encrypted importer ID's. |  | Open |  | Need to discuss options or viability of implementing this function in ACR.
20 | 2015-04-21 | Multiple duplicate SO messages are being sent to truck filers: ACE Cargo Release is seeing significant increase in truck filings which is causing the system to send the same SO message multiple times. |  | Closed |  | ACE Cargo Release will require an update to handle the volume of incoming truck messages. Code updatde, and fix deployed on 4/25/2015
19 | 2015-04-19 | Record Identifier SO50 (Output). The Disposition Code Positions 15-16, overlap with the Narrative Message field Positions 16-56. |  | Closed |  | Need to have the ACE CR IG updated to correct overlapping fields. IG has been updated.
18 | 2015-04-15 | In-bond not in open status, and Entry Port Not the Same as In-bond Dest Port: ACR is editing in-bond data from old bills of lading and rejecting SE transactions based on the closed status of these old bills of lading. |  | Closed |  | Update SE so that it searches for the current in-bond/bill of lading combination. Fix was deployed on 4/27/2015.
17 | 2015-04-14 | SE is rejecting Master Bill of Lading as ineligible for processing: ACR is rejecting Master Airway Bills if they have been previously submitted as FROB type bills. |  | Closed |  | Fix will be deployed on 4/18/2015. Fix deployed on 4/17/2015
16 | 2015-03-30 | Bill Type Validation: Currently ACR does not edit for correct bill type when a filer submits their entry data to CBP. As a resulut, the bill will not be properly displayed. |  | Open |  | On the list to have validation rule added to edit for correct bill type.
15 | 2015-03-11 | Release not posting to manifest. SE UI shows cargo as released, but M1 does not reflect the release. |  | Closed |  | Re-opend issue on 4/7/15. Requires more fixing. Fix deployed on 4/17/2015 at 13:45
11 | 2015-03-10 | SF filed with SE could reject with single transaction importer bond. When the SE is filed with SF using a STB, the stand-alone SF built will reject because does not allow an 01/9 bond combination. |  | Open |  | Need to conduct more research to see if the SF rejects for 01 bond type for STB.
10 | 2015-03-10 | SF rejected for lack of bond information. When SE is filed with SF data, the SF built from the SE is rejected because it does not contain the appropriate bond information. |  | Closed |  | The fix will take the appropriate importer information from the SE10 record in order to populate the bond information in the SF10 record. Fix deployed to ACR Prod on 4/13/2015.
9 | 2015-03-12 | SE built from AE rejects for INVALID BILL QUANTITY UOM. When an AE certified for SE is filed with UOM of "CTNS", the SE is rejected by an edit requiring the UOM to comply with Appendix B. |  | Closed | 2015-03-13
8 | 2015-03-05 | SE built from AE rejects for INVALID LINE NUMBER. When an AE certified for SE is filed with line numbers without leading zeros, the SE is rejected by an edit requiring three numerics for line number. |  | Closed | 2015-03-09
7 | 2015-03-10 | SE built from AE rejects for VALUE LESS THAN ALL LINE ITEM VALUES. When an AE certified for SE is filed with a value without leading zeros, the SE is rejected because the total value is less than the sum of all line values. |  | Open |  | Still waiting on update from SE team.
6 | 2015-03-13 | SE does not release proper piece count for split shipment. SE filed with multiple master/ house combinations, no piece counts released one split part with incorrect piece count. |  | Open |  | SE Team will discuss including more details in the ACR Chapter to mitigate the possibility of confusion from the Trade Community.
5 | 2015-03-12 | CN accepted in SE30 record with both name and number. The CN can only be reported with an identifying number (IRS, SSN) and should be rejected when reported with a name, even if the number is provided. |  | Closed | 2015-04-18 | Currently, SE accepts the SE30 record for CN with both a name and idenifying number. This fix is currently available in CERTIFICATION; Scheduled for PROD deployment 4/18/15. Fix deployed on 4/17/2015.
4 | 2015-03-04 | Inbond deletion is not reflected in all systems. When an inbond is deleted from the Manifest, the deletion is not properly replicated in all systems. This results in a deleted inbond in Manifest, but an active inbond in other systems. SE uses the active inbond for processing, and provides inaccurate results in SO messaging for releases. |  | Closed |  | 3/13/15: Fix deployed to PROD . 3/19/15: Fix pulled back from PROD due to causing other errors. Fix was not pulled back. Fix deployed on 3/13/2015 still stands.
3 | 2015-03-04 | SE not showing cancelled. When an SE is cancelled, the History tab will reflect the cancellation as being accepted by a CBP employee, but the header information still shows the SE as being in its previous status (admissible, released, etc) |  | Closed | 2015-03-14
2 | 2015-02-24 | Ship-To Party not validated. SE does not validate that a ship-to party is presented in the SE transactions. Failure to supply the Ship-To Party will still results in the SE being accepted. |  | Open |  | ACE Cargo Release chapter should be updated to specifiy if Ship To Party is required? SE does not require Ship To, but AE does.
1 | 2015-02-23 | Provisional Release not sent in accurate timeframe. When a bill is modified with an later EDA than the vessel, SE uses this date for provisional release messaging. This date may be later than the vessel's EDA, which causes provisional release messages to be sent late. |  | Open |  | ACE Cargo Release should use the estimated date of arrival of the conveyance, and not the bill of lading.